## API Integration
Sr. No. | Description | Efforts(Hrs)
1 | Vendor Payment Page 1. Table & Page Creation - A new table and page will be developed to record vendor payment entries during the posting of bank payments. 2. Page Actions (Buttons) The page will include three primary action buttons: - HSBC Payment Process - Initiates payment submission to the bank server via API. - Supports two API modes: a) Single Transaction API – for individual payments. b) Bulk Payment API – for batch processing of up to 500 transactions. - Get Transaction Status - Uses the Payment Status Enquiry API to retrieve the current status of submitted payments (Accepted/Rejected). - In case of rejection, the system will capture and store the rejection reason provided by the bank in the Remarks field. - Fetch UTR Number - Retrieves the UTR number for transactions marked as Accepted. - Updates the corresponding payment entry with the UTR details. 3. Batch Processing (Scheduled Job Queue) - A batch report will be implemented to automate status and UTR updates via scheduler. - The job queue will: - Periodically call the Bank Status API to update payment statuses. - If a payment status is updated but the UTR number is missing, the system will invoke the UTR API to fetch and update the UTR. - The scheduler will run at configurable intervals (e.g., every 30 minutes or hourly) | 32
2 | Plain Text Generation for API Integration - Business Central will be enhanced to generate plain text structures containing all required fields for each type of API. - The plain text will be produced using an XMLport, which will transform Business Central data into the ISO 20022 XML V3 format (pain.001.001.03). - This ensures that the system can consistently create the standardized XML payloads needed for secure API communication with HSBC. | 48
3 | Azure Function for Encryption, Decryption, and Authentication 1) Encryption API - Implemented in Azure Functions using .NET code. - Takes the prepared request payload from Business Central. - Encrypts the payload with HSBC’s Public Key. - Encodes the encrypted payload into Base64 format. - Returns the Base64 string to Business Central for inclusion in the API request body. 2) JWT Generation API - Builds the JWT structure using HSBC’s required field definitions. - Generates a hash code for the encrypted request payload. - Constructs the JWT header and payload. - Signs the JWT with the client’s Private Key. - Returns the signed JWT (JWS), which Business Central adds to the Authorization header of the HSBC API request. 3) Decryption API - Processes the HSBC API response, which arrives encrypted and Base64 encoded. - Decodes the response payload from Base64. - Decrypts the decoded payload using the client’s Private Key. - Returns the decrypted acknowledgement or status message. - Business Central maps the decrypted values (e.g., reference ID, status codes, UTR numbers) back to the corresponding transactions. Note :Development Approach - During the initial development phase, the encryption, decryption, and JWT logic will be implemented and tested locally using custom .NET DLLs. - Once validated, the API creation code will be migrated and published as .NET code within Azure Functions, enabling secure and scalable integration with HSBC’s APIs in the Business Central SaaS environment. | 120
4 | FROM CERTIFICATE AUTHORITY (CA): • Purchase SSL certificate from trusted CA - DigiCert, GlobalSign, Entrust, etc. • Get both: 1. Public Certificate (.cer, .pem) 2. Private Key (.key, .pfx with password) • Ensure certificate has: - Your organization name - Proper domain - Minimum 2048-bit RSA - SHA-256 hash (need to purchase by Client) | 0
5 | PGP Certificate Generation and Key Exchange - Generate a PGP key pair (Private Key / Public Key) - Public Key Specification: - Signing algorithm: RSA 2048-bit - Hashing algorithm: SHA-256 - HSBC will provide their Public Key, which will be used to encrypt outbound messages. - Your organization will share its PGP Public Key with HSBC. - When HSBC sends a response, it will be encrypted with your Public Key. You will then use your Private Key to decrypt the response and process the returned data. (need to purchase by Client) | 0
6 | Unit Testing & Issue Resolution | 32
7 | UAT | 4
8 | Production Deployment | 8
9 | Total | 244

## H2H
Sr. No. | Description | Efforts(Hrs)
1 | Vendor Payment Page 1. Table & Page Creation - A new table and page will be developed to record vendor payment entries during the posting of bank payments. 2. Page Actions (Buttons)-Send to HSBC Data Preparation - Process Flow: - Extract payment details from Payment Journal - Validate required fields (Account, Amount, Beneficiary details) - Generate unique Payment Reference ID - Create ISO 20022 compliant XML - Convert XML to Base64 encoding - Prepare JSON payload for Azure Function | 40
2 | AZURE FUNCTION RECEIVES: • Decodes Base64 → Gets XML • PGP Encrypts with HSBC's public key • Signs with our private key • SFTP Uploads to: /Payment_123.pgp | 80
3 | HSBC RECEIVES: • File appears in their SFTP / folder • Decrypts with their private key • Verifies our signature • Processes payment | 0
4 | HSBC SENDS ACKNOWLEDGEMENT: • Creates acknowledgement XML • Encrypts with our public key • Signs with their private key • Places in: /Inbox/ACK_123.pgp | 0
5 | AZURE FUNCTION (scheduled): • Checks /Inbox every 5 minutes • Downloads ACK_123.pgp • Decrypts with our private key • Verifies HSBC's signature • Converts to Base64 • Calls Business Central webhook | 40
6 | BUSINESS CENTRAL RECEIVES: • Gets Base64 acknowledgement • Decodes and parses XML • Updates payment status • Stores UTR number | 32
7 | Unit Testing & Issue Resolution | 32
8 | UAT | 4
9 | Production Deployment | 8
10 | Total | 236